2025 Workplan

| Transformation Strategy 1: Develop Downtown Swainsboro as a destination for family-friendly entertainment. |  |  |  |
| --- | --- | --- | --- |
| Why? The Downtown Development Authority is looking to develop downtown into a retail and entertainment district, which will be anchored by the Barbara & Tobe Karrh Community Arts Center. Establishing downtown as a center for family entertainment will support local businesses, drive economic development, tourism, and strengthen student life for students at local colleges. |  |  |  |
| Goal 1 | Goal 2 | Goal 3 | Goal 4 |
| Develop the Barbara & Tobe Karrh Community Arts Center including the renovation and preservation of the Karrh Center Theater. | Engage more community members in the activities of the DDA. | Develop and maintain community activities that utilize and promote downtown Swainsboro’s unique assets, while providing entertainment and encouraging community spirit. |  |
| Repeat Annual Responsibilities |  |  |  |
| Organize Easter Eggstravaganza Support Pine Tree Festival Organize Christmas Parade Organize and sponsor Freedom Fest Concert & Vendors in conjunction with the Swainsboro Jaycees Red, Wet, & Blue parade and Firework show. Organize Fall Festival Organize the Back-to-School Touch-A-Truck |  |  |  |

| TS1 Goal 1: Continue the development of the Barbara & Tobe Karrh Community Arts Center by completing the renovation of the theater portion of the center, while preserving as much of its historic character as possible and transforming it into a fully functional venue for movies, live performances, and community events. |  | Define Success: Success will be achieved by completing the final phase of the Barbara & Tobe Karrh Community Arts Center—restoring the historic Karrh Center Theater into a fully functional venue for first-run movies, live performances, and community events. This revitalized space will preserve as much of the building’s original character as possible while enhancing and expanding the offerings of the Community Arts Center, which already includes the operational Kalmanson Gallery. |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Partners: Emanuel Coalition for Cultural & Economic Development, City of Swainsboro, Emanuel County Commissioners, Emanuel Arts Council, Chamber of Commerce |  |  |  |  |  |
| Task | Board Member Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Continue working with architects and contractors to complete the renovation phase of the theater. | Mayor Bennett | Melissa Kirby | 06/25 | In Progress | $1,500,000 |
| 2. Complete the installation of the equipment funded by the FY 2025 Georgia Council for the Arts Community Facilities grant. | Ken Warnock | Melissa Kirby | 05/25 | Completed | $150,000 |
| 3. Provide updates on the Karrh Community Arts Center Facebook page to show the progress at the theater. |  | Melissa Kirby | 08/25 | In Progress | $0 |
| 4. Review and update theater website | Anna Gambrell | Melissa Kirby | 12/25 | Ongoing | $0 |
| 5. Develop an operational plan for the theater | Mayor Bennett | Melissa Kirby | 06/25 | Completed | $0 |
| 6. Identify and apply for grants to support Karrh Center project |  | Melissa Kirby | 12/25 | Ongoing | $0 |
| 7. Maintain support of the Karrh Center project by presenting progress presentations to local civic groups. |  | Melissa Kirby | 12/25 | Ongoing | $0 |
| 8. Plan a Theater Event for Donors | Kristin Hall | Melissa Kirby | 08/25 | In Progress | $5,000 |
|  |  |  |  | Total | $1,655,000 |
| TS1 Goal 2: Engage more community members in activities of the DDA |  | Define Success: Increased volunteer and participant base, more diverse group of volunteers and participants |  |  |  |
| Partners: City of Swainsboro, Chamber of Commerce, Emanuel Arts Council, East Georgia State College, Southeastern Technical College, Board of Education |  |  |  |  |  |
| Task | Board Member Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Strengthen relationships with local schools | Nick Robertson | Melissa Kirby | 12/25 | Ongoing | $0 |
| 2. Boost social media efforts | Anna Gambrell | Melissa Kirby | 12/25 | Ongoing | $500 |
| 3. Develop a citizen engagement and volunteer recruitment process. | Kristin Hall | Melissa Kirby | 12/25 | In Progress | $0 |
| 4. Meet & Greet with the DDA board members & staff | Anna Gambrell | Melissa Kirby | 09/25 | In Progress | $500 |
| 5. |  |  |  |  | $0 |
| 6. |  |  |  |  | $0 |
| 7. |  |  |  |  | $0 |
| 8. |  |  |  |  | $0 |
|  |  |  |  | Total | $1,000 |

| TS1 Goal 3: Develop and maintain community activities that utilize and promote downtown Swainsboro’s unique assets, while providing entertainment and encouraging community spirit. |  | Define Success: New events and activities hosted, new businesses opened, more businesses participating in activities and events, more people taking part in downtown events and activities |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Partners: Downtown Businesses, Downtown Property Owners, City of Swainsboro, Recreation Dept., Police Dept., Fire Dept. |  |  |  |  |  |
| Task | Board Member Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Spring Holiday Retail Event | Shaye Davis | Melissa Kirby | 04/25 | Completed | $300 |
| 2. Christmas Open House Holiday Retail Event | Shaye Davis | Melissa Kirby | 11/25 | Completed | $500 |
| 3. Fall Festival Event | Anna Gambrell | Melissa Kirby | 10/25 | Completed | $200 |
| 4. Christmas Parade | Kristin Hall | Melissa Kirby | 12/25 | In Progress | $1,000 |
| 5. Host a series of three concert events downtown. |  | Melissa Kirby | 12/25 | Postponed | $9,000 |
| 6. Work with the local Jaycees to host their 3rd Annual Freedom Fest Downtown. |  | Melissa Kirby | 07/25 | Completed | $2,700 |
| 7. Back to School Touch A Truck Event | Shaye Davis | Melissa Kirby | 08/25 | Completed | $500 |
| 8. Tasks 1-7 are ongoing annual projects. |  |  |  |  | $0 |
| 9. Holiday Market / Taste of Emanuel | Shaye Davis | Melissa Kirby | 04/26 | In Progress | $500 |
| 10. Drive-In Movies to Promote Theater |  | Melissa Kirby | 12/25 | Canceled | $3,000 |
|  |  |  |  | Total | $17,700 |
| TS1 Goal 4: |  | Define Success: |  |  |  |
| Partners: |  |  |  |  |  |
| Task | Board Member Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. |  |  |  |  | $0 |
| 2. |  |  |  |  | $0 |
| 3. |  |  |  |  | $0 |
| 4. |  |  |  |  | $0 |
| 5. |  |  |  |  | $0 |
| 6. |  |  |  |  | $0 |
| 7. |  |  |  |  | $0 |
| 8. |  |  |  |  | $0 |
|  |  |  |  | Total | $0 |

| Transformation Strategy 2: Enhance the appeal, history, and unique characteristics of Downtown Swainsboro through architecture, landscape, and other design improvements |  |  |  |
| --- | --- | --- | --- |
| Why? Preserve downtown’s historic assets and use them to help tell the story of the community. How a place looks and feels has a great bearing on how happy people are there, how involved they are in the community, and it sets the tone for the rest of the community. |  |  |  |
| Goal 1 | Goal 2 | Goal 3 | Goal 4 |
| Maintain seasonal decorations downtown | Review the effectiveness of the façade grant program and continue to promote it to downtown businesses. | Conduct a walking audit of downtown to address concerns of the walkability, cleanliness, and unsightly and nuisance properties of downtown. | Develop a plan to install murals in downtown areas. |
| Repeat Annual Responsibilities |  |  |  |
| Maintain downtown flowers and plantings Decorate the Square for various seasons and holidays |  |  |  |

| TS2 Goal 1: Maintain seasonal decorations downtown |  | Define Success: Ensure downtown is decorated for key seasons/holidays |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Partners: City of Swainsboro, Clearwater Solutions, Design/Decoration Committee |  |  |  |  |  |
| Task | Board Member Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Maintain Wagon on the Square | Kristin Hall | Melissa Kirby Willie Butler | 12/25 | Ongoing | $1,000 |
| 2. Add new Christmas decorations (Christmas lights, wreaths, garland, and new packages.) | Anna Gambrell | Melissa Kirby | 11/25 | In Progress | $6,000 |
| 3. Replace real flowers in hanging baskets with fake flowers. | Anna Gambrell | Melissa Kirby | 12/25 | Postponed | $3,000 |
| 4. Replace 110 Welcome Banners & 110 Christmas Banners |  | Melissa Kirby | 12/25 | Completed | $10,000 |
| 5. |  |  |  |  | $0 |
| 6. |  |  |  |  | $0 |
| 7. |  |  |  |  | $0 |
| 8. |  |  |  |  | $0 |
|  |  |  |  | Total | $20,000 |
| TS2 Goal 2: Review the effectiveness of the façade grant program and continue to promote it to downtown businesses. |  | Define Success: Multiple businesses and property owners apply for façade grants and refresh their properties |  |  |  |
| Partners: City of Swainsboro, Business Owners, Property Owners |  |  |  |  |  |
| Task | Board Member Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Promote the program to business and property owners | Kristin Hall | Melissa Kirby | 12/25 | In Progress | $2,000 |
| 2. Review the effectiveness of the façade grant and make recommendations to the board on how to make the grant more effective while preserving the historic characteristics of downtown. | Anna Gambrell Sara Young | Melissa Kirby | 01/25 | In Progress | $0 |
| 3. |  |  |  |  | $0 |
| 4. |  |  |  |  | $0 |
| 5. |  |  |  |  | $0 |
| 6. |  |  |  |  | $0 |
| 7. |  |  |  |  | $0 |
| 8. |  |  |  |  | $0 |
|  |  |  |  | Total | $2,000 |

| TS2 Goal 3: Annual Review of Downtown |  | Define Success: A clean, safe, and attractive downtown. |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Partners: City of Swainsboro, Clearwater Solutions, Emanuel County Commissioners, Chamber of Commerce, Property Owners, Business Owners, Keep Emanuel Beautiful |  |  |  |  |  |
| Task | Board Member Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Identify any safety issues | Nick Robertson | Melissa Kirby | 12/25 | Ongoing | $0 |
| 2. Identify any unsightly and/or nuisance properties | Nick Robertson | Melissa Kirby | 12/25 | Ongoing | $0 |
| 3. Promote and partner with Keep Emanuel Beautiful to improve the cleanliness of downtown |  | Melissa Kirby | 12/25 | Ongoing | $0 |
| 4. Organize data collected from the walking audit and present findings to the appropriate responsible parties. | Anna Gambrell | Melissa Kirby | 01/26 | In Progress | $0 |
| 5. Work with code enforcement to address the unsightly and nuisance properties | Nick Robertson | Melissa Kirby | 12/25 | Ongoing | $0 |
| 6. |  |  |  |  | $0 |
| 7. |  |  |  |  | $0 |
| 8. |  |  |  |  | $0 |
|  |  |  |  | Total | $0 |
| TS2 Goal 4: Install vibrant, locally inspired murals throughout Downtown Swainsboro to attract visitors, enhance the visual appeal of the area, and celebrate the community’s unique identity and culture. |  | Define Success: The mural installation project will be considered successful when it visibly enhances the aesthetic of Downtown Swainsboro, increases foot traffic and engagement, and fosters community pride and visitor interest. |  |  |  |
| Partners: City of Swainsboro, Keep Emanuel Beautiful, Property Owners, Business Owners, Chamber of Commerce, Emanuel County Commissioners |  |  |  |  |  |
| Task | Board Member Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Identify potential mural locations (public and private buildings downtown) and obtain permission from property owners. | Shaye Davis | Melissa Kirby | 03/25 | Ongoing | $0 |
| 2. Decide on a mural theme (Swainsboro history, community pride, nature, arts) | Anna Gambrell | Melissa Kirby | 08/25 | Completed | $0 |
| 3. Gather community input via surveys, meetings, or social media polls | Shaye Davis | Melissa Kirby | 05/25 | Completed | $0 |
| 4. Build partnerships with local organizations (Emanuel Arts Council, Emanuel Artist Guild, Keep Emanuel Beautiful) |  | Melissa Kirby | 05/25 | Ongoing | $0 |
| 5. Create a project budget (artist fees, supplies, lifts, sealing, marketing) & Explore Funding options. |  | Melissa Kirby | 09/25 | Completed | $0 |
| 6. Wall preparation and installation of mural. | Shaye Davis | Melissa Kirby | 11/25 | Completed | $7,500 |
| 7. Document progress and promote murals online via social media. |  | Melissa Kirby | 12/25 | Completed | $0 |
| 8. |  |  |  |  | $0 |
|  |  |  |  | Total | $7,500 |

| Transformation Strategy 3: Establish partnerships to enhance the activities and impact of the DDA |  |  |  |
| --- | --- | --- | --- |
| Why? In a small town like Swainsboro, it is increasingly important to work with multiple organizations and establish partnerships to meet common goals. |  |  |  |
| Goal 1 | Goal 2 | Goal 3 | Goal 4 |
| Strengthen relationships with local schools | Host quarterly meetings of downtown business owners and explore the possibility of a merchants’ association or other networking organizations | Continuing support of the Emanuel Arts Council | Strengthen relationships with community partners, volunteers, and board members. |
| Repeat Annual Responsibilities |  |  |  |
| Fall Festival Christmas Parade Freedom Fest Concert Pine Tree Festival Present programs for local organizational meetings (such as Rotary, Kiwanis, Exchange Club, etc.) |  |  |  |

| TS3 Goal 1: Strengthen relationships with local schools. |  | Define Success: Increase student involvement in downtown events. |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Partners: Emanuel Co. Board of Education, East Georgia State College, Southeastern Technical College |  |  |  |  |  |
| Task | Board Member Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Boost social media presence |  | Melissa Kirby | 12/25 | Ongoing | $100 |
| 2. Host an event in partnership with a local college to appeal to students | Anna Gambrell Sara Young | Melissa Kirby | 12/25 | In Progress | $0 |
| 3. Develop High School & College Leadership Program | Anna Gambrell | Melissa Kirby | 12/25 | In Progress | $0 |
| 4. |  |  |  |  | $0 |
| 5. |  |  |  |  | $0 |
| 6. |  |  |  |  | $0 |
| 7. |  |  |  |  | $0 |
| 8. |  |  |  |  | $0 |
|  |  |  |  | Total | $0 |
| TS3 Goal 2: Host quarterly meetings of downtown business owners and explore possibility of merchants’ association or other networking organizations. |  | Define Success: Seeing business owners come together to develop and execute their ideals. Develop merchants’ associations to help boost retail activities and increase networking. |  |  |  |
| Partners: City of Swainsboro, Downtown Business Owners |  |  |  |  |  |
| Task | Board Member Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Host quarterly meetings to discuss upcoming events and activities and gain retailer input | Shaye Davis | Melissa Kirby | 12/25 | Ongoing | $0 |
| 2. Offer educational opportunities for downtown business owners | Mayor Bennett | Melissa Kirby | 12/25 | In Progress | $0 |
| 3. |  |  |  |  | $0 |
| 4. |  |  |  |  | $0 |
| 5. |  |  |  |  | $0 |
| 6. |  |  |  |  | $0 |
| 7. |  |  |  |  | $0 |
| 8. |  |  |  |  | $0 |
|  |  |  |  | Total | $0 |

| TS3 Goal 3: Continue support of the Emanuel Arts Council |  | Define Success: A thriving, successful arts center to attract visitors to the downtown area. |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Partners: City of Swainsboro, Emanuel Arts Council, Emanuel Artists Guild, Chamber of Commerce |  |  |  |  |  |
| Task | Board Member Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Boost social media presence | Ken Warnock | Melissa Kirby | 12/25 | Ongoing | $0 |
| 2. Provide and maintain a space at the Karrh Community Arts Center to house the Emanuel Arts Council | Mayor Bennett | Melissa Kirby | 12/25 | Ongoing | $0 |
| 3. Promote and partner with the Emanuel Arts Council to provide art events at the center. | Sara Young | Melissa Kirby | 12/25 | Ongoing | $0 |
| 4. |  |  |  |  | $0 |
| 5. |  |  |  |  | $0 |
| 6. |  |  |  |  | $0 |
| 7. |  |  |  |  | $0 |
| 8. |  |  |  |  | $0 |
|  |  |  |  | Total | $0 |
| TS3 Goal 4: Strengthen relationships with community partners, volunteers, and board members through a successfully trained DDA board. |  | Define Success: A successfully trained board working with community partners, volunteers, and other board members to promote the continued success of Main Street Approach in our community. |  |  |  |
| Partners: City of Swainsboro, Chamber of Commerce |  |  |  |  |  |
| Task | Board Member Responsible | Staff Responsible | Due Date | Progress | Budget |
| 1. Develop a DDA board manual containing all pertinent information regarding DDA. | Anna Gambrell | Melissa Kirby | 12/25 | In Progress | $0 |
| 2. Develop new board member onboard training | Anna Gambrell | Melissa Kirby | 12/25 | In Progress | $0 |
| 3. Create a new board member recruitment process. | Anna Gambrell | Melissa Kirby | 12/25 | In Progress | $0 |
| 4. |  |  |  |  | $0 |
| 5. |  |  |  |  | $0 |
| 6. |  |  |  |  | $0 |
| 7. |  |  |  |  | $0 |
| 8. |  |  |  |  | $0 |
|  |  |  |  | Total | $0 |